# NPA 514 RELIEF PLANNING COMMITTEE - TIF REPORT

Date Submitted: 	 22 November 2002

WORKING GROUP:  NPA 514 Relief Planning Committee (Ad Hoc)

REPORT #:	005						File ID:  514RE05A.doc

REPORT TITLE:	Recommendation to Delay NPA 514 Relief Date from February 2004 to September 2005

OUTCOME: 	Consensus

RELATED TASK(s) #:	None

BACKGROUND:

Numbering Plan Area (NPA) 514 Relief Planning was initiated in May 2000 when the Canadian Numbering Administrator (CNA) announced, based on the aggregate results of the 2000 Central Office Code Utilization Survey (COCUS) which is based on Telecommunications Service Provider (TSP) inputs, that NPA 514 was forecast to exhaust in the second quarter of 2004.  The CNA commenced relief activities to develop the Initial Planning Document (IPD).  Subsequently, a Relief Planning Committee (RPC) was created as an Ad Hoc Committee of the CRTC Interconnection Steering Committee (CISC) to identify and assess the various NPA Relief Methods.  The RPC recommended that an overlay be implemented to provide relief for the 514 area.  On 22 December 2000, the Canadian Radio-television and Telecommunications Commission (CRTC or Commission) issued Order CRTC 2000-1187 that directed a new overlay area code in the 514 region be implemented on 7 June 2003 (which was 12 months in advance of the then Projected Exhaust Date of June 2004).

Subsequent COCUS results indicated that the Projected Exhaust Date for NPA 514 would not occur until about April or May 2005.  Consequently, on 14 May 2001, Bell Canada requested the CRTC to Review and Vary the above Order to change the Relief Date, among other things, pending results of the next two Special COCUSes (S-COCUS).

In response to the application to Review and Vary Order CRTC 2000-1187, on 15 October 2001 the Commission issued Decision CRTC 2001-648.  In this Decision, the Commission concluded there was sufficient evidence to warrant a deferral of the Relief Date to 7 February 2004 (about 14 to 18 months in advance of the then Projected Exhaust Date of April-August 2005).  Subsequently, the CRTC approved the revised Relief Implementation Plan (RIP) on 13 March 2002 (Telecom Decision CRTC 2002-15).

In accordance with the approved NPA 514 RIP, Consumer Awareness activities commenced in September 2002 with a news release and print advertisements in the major daily newspapers.  Certain service providers have also commenced bill insert activities.  In addition, on 18 March 2002, the North American Numbering Plan Administrator (NANPA) posted Planning Letter (PL) 315 concerning the overlay in NPA 514.

Summary of Projected Exhaust Dates

The table below summarizes the Projected Exhaust Dates for NPA 514 from the various surveys (COCUS and Numbering Resource Utilization Forecasts (NRUFs)) that have been conducted by the CNA.  Based on the 18 September 2002 Special NRUF (S-NRUF), the current Relief Date of 4 February 2004 is a full 31 months prior to the current Projected Exhaust Date of September 2006.

| NPA 514 Summary of Projected Exhaust Dates |
| --- |
| NPA | Type of C-NRUF | Date of Publication | Projected Exhaust Date |
| 514 | 2000 G – COCUS | 9 May 2000 | May 2004 |
| 514 | 2000 R – COCUS | 28 June 2000 | June 2004 |
| 514 | 2000 G – COCUS (revision) | 28 July 2000 | June 2004 |
| 514 | 2001 R – COCUS | 26 January 2001 | April 2005 |
| 514 | 2001 G – COCUS | 10 April 2001 | May 2005 |
| 514 | 2001 S – COCUS | 27 April 2001 | August 2005 |
| 514 | 2001 S – COCUS | July 2001 | April 2005 |
| 514 | 2001 S – COCUS | 26-27 October 2001 | June 2005 |
| 514 | 2001 S – COCUS | 27 March 2002 | June 2006 |
| 514 | 2002 S – NRUF/ G – NRUF | 1 May 2002 | April 2006 |
| 514 | 2002 S – NRUF | 18 September 2002 | September 2006 |

The Relief Planning Committee noted that if an average of the last three S-COCUS/S-NRUF results were used, then the average Projected Exhaust Date would be mid-June 2006 or 28.3 months between the Commission’s mandated Relief Date of February 7, 2004 and the June 2006 averaged Projected Exhaust Date.  The Relief Planning Committee also notes that if the actual usage of CO Codes of 40-45 CO Codes per year is used to forecast the Projected Exhaust Date, the Projected Exhaust Date would be moved outwards by up to about one year from September 2006 to August 2007.

The CNA’s projections of NPA exhaust that have been issued after Decision CRTC 2001-648 (15 October 2001) confirm that the Projected Exhaust Date for NPA 514 has been extended outwards significantly to the second or third quarter of 2006.  These projections indicate that there is a 31 month interval between the Commission’s mandated Relief Date of 7 February 2004 and the recent Projected Exhaust Date of September 2006.

Concerns Regarding the Projected Exhaust Date

As a result of a recent review of the above projections and actual Central Office (CO) Code assignments in NPA 514, the RPC notes that the Projected Exhaust Date has been extended outwards on a consistent basis over the last few years from 2004 to 2005 and recently to 2006.

The RPC submits that the underlying economic and competitive market environment of the Canadian telecommunications industry has changed substantially during the latter part of 2001 and 2002, causing several TSPs to restructure their financial arrangements, or cease operating entirely.  Consequently, any opportunity to defer costs or investments, such as the inherent costs in implementing a new overlay NPA, would be of significant value to the industry at this time.

Changes to Relief Dates

Section 4.15 of the Canadian NPA Relief Planning Guidelines states:

The RPC shall establish a Relief Date that is 12 to 18 months in advance of the Projected Exhaust Date, at the time the Planning Document is submitted to the CISC and CRTC.  If the Projected Exhaust Date advances or is deferred significantly (i.e. 6 months or more) from the established Exhaust Date, and such an advancement or deferral is identified in the first 36 months of the 72 month Relief Planning window, the RPC may recommend to the Commission a change to the established Relief Date via the CISC process.

The above clause permits the RPC to recommend a change to the established Relief Date via the CISC process, provided that the advancement or deferral is significant (i.e., 6 months or more) and is identified within the first 36 months of the 72 month Relief Planning window.  In this case, all the pertinent criteria to propose a change to the Relief Date are met.  The mid-year 2002 S-NRUF forecast indicates that exhaust is deferred about 12 months from the April-August 2005 time frame to the April-September 2006 time frame.  As Relief Planning was initiated in May 2000, this request for a deferral of the NPA relief project is within the first 36 months of the Relief Planning window.

Rationale for Delaying the Relief Date

1)	Implementation Interval Longer than Required

The current Relief Date of 7 February  2004 is a full 31 months prior to the current Projected Exhaust Date of September 2006.  The RPC submits that such an interval is excessive and that there is an opportunity to defer the Relief Date to September 2005.  The following chart illustrates that a time interval of 12-18 months has been consistently applied in previous overlay decisions:

| NPA | Decision | Relief Date | Projected Exhaust Date | Implementation Interval |
| --- | --- | --- | --- | --- |
| 604 | Order 2000-786 | Nov 2001 | Jan 2003 | 14 months |
| 613 | Order 2001-841 | 3Q 2008 | 4Q 2009 | 12 to 15 months |
| 514 | Order 2000-1187 | Jun 2003 | June 2004 | 12 months |
| 519 | Decision 2002-25 | 1Q 2005 | 2Q 2006 | 12 to 15 months |
| 514 R&V | Decision 2001-648 | Feb 2004 | April 2005 | 14 months |
| 514 Status |  | Feb 2004 | Sept 2006 | 31 months |

2)	Deferral would Benefit Both Customers and Carriers

As the implementation of NPA relief is an expensive and disruptive process for both customers and carriers, the RPC requests that the 7 February 2004 Relief Date be modified to September 2005.  The RPC submits that a delay would benefit customers by providing additional time to complete the activities that they are required to do, such as reprogramming telecommunications equipment (speed dialers, fax machines, security and alarm company facilities) and updating stationary to reflect the 10-digit telephone numbers.  Carriers would benefit significantly as the costs to implement and test network modifications and to fund communication campaigns would also be deferred at a time when virtually all carriers are being affected by the competitive environment.  TSPs would have the opportunity to defer costs in this time of severe capital constraints and economic uncertainties.  Furthermore, based on the current data, the proposed deferral would still provide sufficient time for relief to be implemented in advance of the new Projected Exhaust Date.

RECOMMENDATIONS:

As a change to the Relief Date would have the benefit of delaying the costs of implementing relief for all customers and TSPs operating in area code 514 by one year and seven months, the RPC submits the following recommendations to the CISC:

- Submit a recommendation to the CRTC to modify the Relief Date of 7 February 2004 to September 2005.

- The CRTC direct the RPC to reconvene at an appropriate time to change the RIP including the relief implementation schedule and associated Consumer Awareness Program and Planning Letter.

- The Commission direct the RPC to monitor the future S-NRUF results and actual CO Code assignments, and to advise the Commission when and if any further deferral or advance of the Relief Date would be warranted.

- Direct the RPC to request the Consumer Awareness Task Force and the TSPs to revise the Consumer Awareness Program to ensure customers are advised of the new Relief Date and the date for commencement of network dialing announcements.

Accordingly, the RPC submits that it would be in the public interest to delay the implementation of relief for NPA 514 and proposes that the CISC endorse such a proposal for submission to the Commission for approval.  The RPC requests the CISC and CRTC to address these recommendations in an expeditious manner, so that the RPC and TSPs can make the necessary changes to the RIP and associated implementation activities, some of which have already commenced.